## Task Breakdown POS RDI
DETAIL TASK BREAKDOWN — IMPLEMENTASI SISTEM POS PT RASA DISTRIBUSI INDONESIA (RDI)
Breakdown task per milestone mengacu ke Referensi Timeline BRD (2 Bulan / 8 Minggu, Agustus 2026) — bersifat indikatif, dapat menyesuaikan hasil discovery/requirement final
No | Akt. # | Fase | Minggu | Aktivitas Utama (Timeline) | Detail Task | PIC | Deliverable / Output | Status
1 | 1 | Fase 1: Discovery & Setup | W1 | Kick-off & alignment stakeholder | Kick-off meeting dengan stakeholder RDI (IT, Brand & Marketing, Outlet Ops) | Project Manager | MoM, Project Charter | Belum Mulai
2 | 1 | Fase 1: Discovery & Setup | W1 | Kick-off & alignment stakeholder | Penyusunan & sirkulasi Project Charter | Project Manager | MoM, Project Charter | Belum Mulai
3 | 1 | Fase 1: Discovery & Setup | W1 | Kick-off & alignment stakeholder | Penyusunan Minutes of Meeting (MoM) kick-off | Project Manager | MoM, Project Charter | Belum Mulai
4 | 1 | Fase 1: Discovery & Setup | W1 | Kick-off & alignment stakeholder | Konfirmasi struktur tim proyek & PIC masing-masing pihak | Project Manager | MoM, Project Charter | Belum Mulai
5 | 2 | Fase 1: Discovery & Setup | W1-W2 | Requirement finalization POS (table, order, role) | Review & validasi requirement Table Management dengan Outlet Ops | BA / Consultant | Dokumen requirement final | Belum Mulai
6 | 2 | Fase 1: Discovery & Setup | W1-W2 | Requirement finalization POS (table, order, role) | Review & validasi requirement Order/Kasir multi-channel (dine-in, online, pickup) | BA / Consultant | Dokumen requirement final | Belum Mulai
7 | 2 | Fase 1: Discovery & Setup | W1-W2 | Requirement finalization POS (table, order, role) | Review & validasi requirement Role POS (Cashier, Captain Order, Bar Checker, Kitchen Checker) | BA / Consultant | Dokumen requirement final | Belum Mulai
8 | 2 | Fase 1: Discovery & Setup | W1-W2 | Requirement finalization POS (table, order, role) | Finalisasi & sign-off Dokumen Requirement final | BA / Consultant | Dokumen requirement final | Belum Mulai
9 | 3 | Fase 1: Discovery & Setup | W1-W2 | Data mapping outlet, meja, menu, kategori item | Kumpulkan data master outlet (denah & kapasitas meja per outlet) | BA + Outlet Ops | Master data sheet | Belum Mulai
10 | 3 | Fase 1: Discovery & Setup | W1-W2 | Data mapping outlet, meja, menu, kategori item | Kumpulkan data master menu & kategori item (makanan, minuman, snack, bundling) | BA + Outlet Ops | Master data sheet | Belum Mulai
11 | 3 | Fase 1: Discovery & Setup | W1-W2 | Data mapping outlet, meja, menu, kategori item | Pemetaan kategori item ke station printer (kitchen/bar) | BA + Outlet Ops | Master data sheet | Belum Mulai
12 | 3 | Fase 1: Discovery & Setup | W1-W2 | Data mapping outlet, meja, menu, kategori item | Susun Master Data Sheet (outlet, meja, menu, kategori) | BA + Outlet Ops | Master data sheet | Belum Mulai
13 | 4 | Fase 1: Discovery & Setup | W2 | Setup environment Zoho Creator (POS custom app) | Provisioning environment Zoho Creator untuk custom app POS | Zoho Admin / Dev | Environment siap | Belum Mulai
14 | 4 | Fase 1: Discovery & Setup | W2 | Setup environment Zoho Creator (POS custom app) | Setup struktur form & report dasar per modul (Table, Order, Inventory, dll) | Zoho Admin / Dev | Environment siap | Belum Mulai
15 | 4 | Fase 1: Discovery & Setup | W2 | Setup environment Zoho Creator (POS custom app) | Konfigurasi akses developer & environment testing | Zoho Admin / Dev | Environment siap | Belum Mulai
16 | 4 | Fase 1: Discovery & Setup | W2 | Setup environment Zoho Creator (POS custom app) | Verifikasi environment siap untuk mulai development | Zoho Admin / Dev | Environment siap | Belum Mulai
17 | 5 | Fase 2: Dev. Frontend POS | W3 | Development Table Management (denah & status meja) | Build visual floor plan/denah meja per outlet | Dev | Modul table management aktif | Selesai
18 | 5 | Fase 2: Dev. Frontend POS | W3 | Development Table Management (denah & status meja) | Implementasi status meja real-time (Tersedia, Terisi, Reserved) | Dev | Modul table management aktif | Selesai
19 | 5 | Fase 2: Dev. Frontend POS | W3 | Development Table Management (denah & status meja) | Implementasi fitur pindah meja (table transfer) dalam satu sesi order | Dev | Modul table management aktif | Selesai
20 | 5 | Fase 2: Dev. Frontend POS | W3 | Development Table Management (denah & status meja) | Implementasi fitur merge/split meja untuk rombongan besar | Dev | Modul table management aktif | Selesai
21 | 5 | Fase 2: Dev. Frontend POS | W3 | Development Table Management (denah & status meja) | Unit testing modul Table Management | Dev | Modul table management aktif | Sebagian
22 | 6 | Fase 2: Dev. Frontend POS | W3-W4 | Development Order/Kasir multi-channel (dine-in/online/pickup) | Build satu antarmuka input order untuk dine-in, online, dan pickup | Dev | Modul order aktif | Selesai
23 | 6 | Fase 2: Dev. Frontend POS | W3-W4 | Development Order/Kasir multi-channel (dine-in/online/pickup) | Integrasi antrian order dari Webstore Rasa Connect ke POS | Dev | Modul order aktif | Belum
24 | 6 | Fase 2: Dev. Frontend POS | W3-W4 | Development Order/Kasir multi-channel (dine-in/online/pickup) | Implementasi status order per channel (baru, diproses, siap, selesai) | Dev | Modul order aktif | Selesai
25 | 6 | Fase 2: Dev. Frontend POS | W3-W4 | Development Order/Kasir multi-channel (dine-in/online/pickup) | Implementasi estimasi waktu penyelesaian order pickup/online | Dev | Modul order aktif | Selesai
26 | 6 | Fase 2: Dev. Frontend POS | W3-W4 | Development Order/Kasir multi-channel (dine-in/online/pickup) | Integrasi cart dengan modul promo/bundling | Dev | Modul order aktif | Selesai
27 | 6 | Fase 2: Dev. Frontend POS | W3-W4 | Development Order/Kasir multi-channel (dine-in/online/pickup) | Unit testing modul Order/Kasir | Dev | Modul order aktif | Selesai
28 | 7 | Fase 2: Dev. Frontend POS | W4 | Konfigurasi Printer Allocation per station | Konfigurasi printer per station (kasir, bar, kitchen) | Dev + Outlet Ops | Print routing aktif | Selesai
29 | 7 | Fase 2: Dev. Frontend POS | W4 | Konfigurasi Printer Allocation per station | Setup auto-routing print order berdasarkan kategori item | Dev + Outlet Ops | Print routing aktif | Selesai
30 | 7 | Fase 2: Dev. Frontend POS | W4 | Konfigurasi Printer Allocation per station | Setup dukungan multi-printer dalam satu outlet | Dev + Outlet Ops | Print routing aktif | Selesai
31 | 7 | Fase 2: Dev. Frontend POS | W4 | Konfigurasi Printer Allocation per station | Implementasi fitur reprint order untuk koreksi/duplikat | Dev + Outlet Ops | Print routing aktif | Selesai
32 | 7 | Fase 2: Dev. Frontend POS | W4 | Konfigurasi Printer Allocation per station | Testing print routing di outlet pilot | Dev + Outlet Ops | Print routing aktif | Belum
33 | 8 | Fase 2: Dev. Frontend POS | W4 | Setup role-based access (Cashier/Captain/Bar/Kitchen Checker) | Setup role-based login & access control per fungsi | Dev | Role matrix aktif | Selesai
34 | 8 | Fase 2: Dev. Frontend POS | W4 | Setup role-based access (Cashier/Captain/Bar/Kitchen Checker) | Konfigurasi hak akses Cashier (pembayaran & cetak struk) | Dev | Role matrix aktif | Selesai
35 | 8 | Fase 2: Dev. Frontend POS | W4 | Setup role-based access (Cashier/Captain/Bar/Kitchen Checker) | l | Dev | Role matrix aktif | Selesai
36 | 8 | Fase 2: Dev. Frontend POS | W4 | Setup role-based access (Cashier/Captain/Bar/Kitchen Checker) | Konfigurasi hak akses Bar Checker & Kitchen Checker (verifikasi item) | Dev | Role matrix aktif | Selesai
37 | 8 | Fase 2: Dev. Frontend POS | W4 | Setup role-based access (Cashier/Captain/Bar/Kitchen Checker) | Implementasi audit trail aktivitas per role/user | Dev | Role matrix aktif | Selesai
38 | 8 | Fase 2: Dev. Frontend POS | W4 | Setup role-based access (Cashier/Captain/Bar/Kitchen Checker) | Testing role matrix & access control | Dev | Role matrix aktif | Sebagian
39 | 9 | Fase 3: Dev. Backend & Integrasi | W5 | Development Outlet Inventory (stock opname, wastage, transfer) | Build modul stock opname per outlet dengan pencatatan selisih | Dev | Modul inventory aktif | Selesai
40 | 9 | Fase 3: Dev. Backend & Integrasi | W5 | Development Outlet Inventory (stock opname, wastage, transfer) | Build modul pencatatan wastage dengan kategori/alasan | Dev | Modul inventory aktif | Selesai
41 | 9 | Fase 3: Dev. Backend & Integrasi | W5 | Development Outlet Inventory (stock opname, wastage, transfer) | Build modul transfer stok in/out antar outlet & gudang pusat | Dev | Modul inventory aktif | Selesai
42 | 9 | Fase 3: Dev. Backend & Integrasi | W5 | Development Outlet Inventory (stock opname, wastage, transfer) | Implementasi update stok real-time setiap transaksi penjualan | Dev | Modul inventory aktif | Selesai
43 | 9 | Fase 3: Dev. Backend & Integrasi | W5 | Development Outlet Inventory (stock opname, wastage, transfer) | Implementasi notifikasi stok menipis (reorder level) per outlet | Dev | Modul inventory aktif | Selesai
44 | 10 | Fase 3: Dev. Backend & Integrasi | W5 | Development Production Semi Finished Goods (BOM 4 level) | Build struktur BOM hingga 4 level (raw material -> semi-finished -> finished good) | Dev | Modul BOM aktif | Selesai
45 | 10 | Fase 3: Dev. Backend & Integrasi | W5 | Development Production Semi Finished Goods (BOM 4 level) | Implementasi pengurangan stok bahan baku otomatis saat produksi | Dev | Modul BOM aktif | Selesai
46 | 10 | Fase 3: Dev. Backend & Integrasi | W5 | Development Production Semi Finished Goods (BOM 4 level) | Implementasi pencatatan hasil produksi (yield) & konversi satuan | Dev | Modul BOM aktif | Selesai
47 | 10 | Fase 3: Dev. Backend & Integrasi | W5 | Development Production Semi Finished Goods (BOM 4 level) | Setup dukungan produksi di Central Kitchen & dapur outlet | Dev | Modul BOM aktif | Selesai
48 | 10 | Fase 3: Dev. Backend & Integrasi | W5 | Development Production Semi Finished Goods (BOM 4 level) | Implementasi traceability batch produksi semi-finished goods | Dev | Modul BOM aktif | Selesai
49 | 11 | Fase 3: Dev. Backend & Integrasi | W5-W6 | Development Marketing/Disc/Bundle & Loyalty Program | Build konfigurasi diskon persentase & nominal per item/kategori | Dev | Promo & loyalty aktif | Selesai
50 | 11 | Fase 3: Dev. Backend & Integrasi | W5-W6 | Development Marketing/Disc/Bundle & Loyalty Program | Build konfigurasi paket bundling multi-produk dengan harga khusus | Dev | Promo & loyalty aktif | Selesai
51 | 11 | Fase 3: Dev. Backend & Integrasi | W5-W6 | Development Marketing/Disc/Bundle & Loyalty Program | Implementasi penjadwalan periode promo (tanggal & jam berlaku) | Dev | Promo & loyalty aktif | Selesai
52 | 11 | Fase 3: Dev. Backend & Integrasi | W5-W6 | Development Marketing/Disc/Bundle & Loyalty Program | Build fitur registrasi member baru & akumulasi poin otomatis dari POS | Dev | Promo & loyalty aktif | Selesai
53 | 11 | Fase 3: Dev. Backend & Integrasi | W5-W6 | Development Marketing/Disc/Bundle & Loyalty Program | Implementasi penukaran reward/poin langsung saat transaksi | Dev | Promo & loyalty aktif | Selesai
54 | 11 | Fase 3: Dev. Backend & Integrasi | W5-W6 | Development Marketing/Disc/Bundle & Loyalty Program | Testing modul promo & loyalty end-to-end | Dev | Promo & loyalty aktif | Selesai
55 | 12 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Backend Reporting (Zoho Analytics/Books) | Setup sinkronisasi otomatis data transaksi POS ke Zoho Analytics/Books | Dev + BA | Dashboard live | Belum
56 | 12 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Backend Reporting (Zoho Analytics/Books) | Build laporan penjualan per outlet, per produk/kategori, per periode | Dev + BA | Dashboard live | Selesai
57 | 12 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Backend Reporting (Zoho Analytics/Books) | Build laporan performa program promosi/diskon/bundle | Dev + BA | Dashboard live | Selesai
58 | 12 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Backend Reporting (Zoho Analytics/Books) | Setup dashboard KPI penjualan & tren (sinkron Zoho Analytics) | Dev + BA | Dashboard live | Sebagian
59 | 12 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Backend Reporting (Zoho Analytics/Books) | Validasi akurasi data laporan vs transaksi sumber | Dev + BA | Dashboard live | Sebagian
60 | 13 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Webstore Rasa Connect & Jubelio | Konfigurasi Zoho Flow untuk mapping data antar Rasa POS, Webstore Rasa Connect, Jubelio, dan Zoho One | Dev + IT | Integrasi aktif | Belum
61 | 13 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Webstore Rasa Connect & Jubelio | Setup alur order to cash: validasi data -> update Inventory & CRM -> invoice Books -> sinkron Analytics | Dev + IT | Integrasi aktif | Belum
62 | 13 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Webstore Rasa Connect & Jubelio | Setup validasi transaksi, retry proses, monitoring & notifikasi error di Zoho Flow | Dev + IT | Integrasi aktif | Belum
63 | 13 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Webstore Rasa Connect & Jubelio | Sinkronisasi data customer & histori pembelian ke Zoho CRM | Dev + IT | Integrasi aktif | Belum
64 | 13 | Fase 3: Dev. Backend & Integrasi | W6 | Integrasi Webstore Rasa Connect & Jubelio | Testing end-to-end integrasi lintas channel (dine-in, online, pickup, marketplace) | Dev + IT | Integrasi aktif | Belum
65 | 14 | Fase 4: UAT, Training & Go-Live | W7 | Persiapan skenario UAT & test script | Susun skenario test per modul (Table Mgmt, Order, Inventory, BOM, Promo/Loyalty, Reporting) | BA / QA | UAT plan dokumen | Belum Mulai
66 | 14 | Fase 4: UAT, Training & Go-Live | W7 | Persiapan skenario UAT & test script | Susun test script per role (Cashier, Captain Order, Bar Checker, Kitchen Checker) | BA / QA | UAT plan dokumen | Belum Mulai
67 | 14 | Fase 4: UAT, Training & Go-Live | W7 | Persiapan skenario UAT & test script | Siapkan data uji (outlet, menu, member, promo) untuk UAT | BA / QA | UAT plan dokumen | Belum Mulai
68 | 14 | Fase 4: UAT, Training & Go-Live | W7 | Persiapan skenario UAT & test script | Finalisasi & distribusi dokumen UAT plan ke tim outlet | BA / QA | UAT plan dokumen | Belum Mulai
69 | 15 | Fase 4: UAT, Training & Go-Live | W7 | UAT per role (Cashier, Captain Order, Bar & Kitchen Checker) | Eksekusi UAT modul Table Management & Order/Kasir multi-channel | QA + Outlet Team | UAT sign-off | Belum
70 | 15 | Fase 4: UAT, Training & Go-Live | W7 | UAT per role (Cashier, Captain Order, Bar & Kitchen Checker) | Eksekusi UAT modul Kitchen/Bar Display & printer routing | QA + Outlet Team | UAT sign-off | Belum
71 | 15 | Fase 4: UAT, Training & Go-Live | W7 | UAT per role (Cashier, Captain Order, Bar & Kitchen Checker) | Eksekusi UAT modul Payment (metode pembayaran, redeem loyalty, cetak struk) | QA + Outlet Team | UAT sign-off | Belum
72 | 15 | Fase 4: UAT, Training & Go-Live | W7 | UAT per role (Cashier, Captain Order, Bar & Kitchen Checker) | Eksekusi UAT modul Inventory, Production BOM, dan Reporting | QA + Outlet Team | UAT sign-off | Belum
73 | 15 | Fase 4: UAT, Training & Go-Live | W7 | UAT per role (Cashier, Captain Order, Bar & Kitchen Checker) | Pencatatan defect/isu & retest hasil perbaikan | QA + Outlet Team | UAT sign-off | Belum
74 | 15 | Fase 4: UAT, Training & Go-Live | W7 | UAT per role (Cashier, Captain Order, Bar & Kitchen Checker) | Sign-off UAT oleh PIC pelanggan | QA + Outlet Team | UAT sign-off | Belum
75 | 16 | Fase 4: UAT, Training & Go-Live | W7 | Pelatihan user per outlet (champion user) | Susun training material per role (Cashier, Captain Order, Bar/Kitchen Checker, Admin Console) | Trainer / BA | Training material | Belum
76 | 16 | Fase 4: UAT, Training & Go-Live | W7 | Pelatihan user per outlet (champion user) | Training champion user per outlet | Trainer / BA | Training material | Belum
77 | 16 | Fase 4: UAT, Training & Go-Live | W7 | Pelatihan user per outlet (champion user) | Sesi hands-on/simulasi transaksi di lingkungan training | Trainer / BA | Training material | Belum
78 | 16 | Fase 4: UAT, Training & Go-Live | W7 | Pelatihan user per outlet (champion user) | Evaluasi kesiapan user pasca training | Trainer / BA | Training material | Belum
79 | 17 | Fase 4: UAT, Training & Go-Live | W7-W8 | Migrasi data awal & validasi | Migrasi data master (outlet, meja, menu, kategori item, customer/member) | Dev + BA | Data migration done | Sebagian
80 | 17 | Fase 4: UAT, Training & Go-Live | W7-W8 | Migrasi data awal & validasi | Migrasi data stok awal per outlet | Dev + BA | Data migration done | Sebagian
81 | 17 | Fase 4: UAT, Training & Go-Live | W7-W8 | Migrasi data awal & validasi | Validasi kesesuaian data hasil migrasi vs sumber data | Dev + BA | Data migration done | Belum
82 | 17 | Fase 4: UAT, Training & Go-Live | W7-W8 | Migrasi data awal & validasi | Rekonsiliasi data sebelum go-live | Dev + BA | Data migration done | Belum
83 | 18 | Fase 4: UAT, Training & Go-Live | W8 | Go-live pilot outlet & hypercare support | Go-live di outlet pilot (sesuai kesepakatan) | PM + Dev | Go-live approved | Belum
84 | 18 | Fase 4: UAT, Training & Go-Live | W8 | Go-live pilot outlet & hypercare support | Monitoring transaksi & sinkronisasi data real-time pasca go-live | PM + Dev | Go-live approved | Belum
85 | 18 | Fase 4: UAT, Training & Go-Live | W8 | Go-live pilot outlet & hypercare support | Hypercare support (respon cepat isu operasional outlet) | PM + Dev | Go-live approved | Belum
86 | 18 | Fase 4: UAT, Training & Go-Live | W8 | Go-live pilot outlet & hypercare support | Evaluasi hasil go-live pilot & persiapan rollout outlet berikutnya | PM + Dev | Go-live approved | Belum
87 | 18 | Fase 4: UAT, Training & Go-Live | W8 | Go-live pilot outlet & hypercare support | Approval/sign-off go-live oleh pelanggan | PM + Dev | Go-live approved | Belum
Catatan timeline (BRD): Total durasi 8 minggu (2 bulan) · Development W1-W6 · UAT & Training W7 · Go-Live target minggu ke-8 setelah UAT sign-off.